## Sheet1
In Lab? | Year | Month | Day | Start | End | Total Time | Description
YES | 2021 | 9 | 21 | 12:30 | 15:00 | 2:30 | Read Ch 6 & its four lab assignments. Familiarized myself with the start up, shut down, and jogging procedures of the FANUC machine.
YES | 2021 | 9 | 23 | 13:30 | 15:45 | 2:15 | Skimmed Ch 7, read Ch 8, completed Procedure 8-1, completed Lab 7, but disregarded Procedure 8-2.
YES | 2021 | 9 | 28 | 13:45 | 15:30 | 1:45 | Completed Lab 8, read Ch 9, completed Lab 9.
YES | 2021 | 10 | 12 | 13:30 | 15:45 | 2:15 | Skimmed Ch 8 & 9, read Ch 10. Experimented with robot.
YES | 2021 | 10 | 14 | 14:00 | 15:45 | 1:45 | Read Ch 11, 12, & 13. Experimented with robot.
YES | 2021 | 10 | 19 | 13:30 | 15:30 | 2:00 | Read Ch 14 & 15. Experimented with robot.
YES | 2021 | 10 | 26 | 14:15 | 16:30 | 2:15 | Taught Tool Frames and Jog Frames for SWAP_CYLNDRS program.
YES | 2021 | 10 | 28 | 13:30 | 16:30 | 3:00 | Teaching SWAP_CYLNDRS program.
YES | 2021 | 11 | 2 | 12:45 | 14:15 | 1:30 | Finished prototyping SWAP_CYLNDRS program.
YES | 2021 | 11 | 4 | 13:30 | 16:15 | 2:45 | Fixed speed and space tolerances of SWAP_CYLNDRS program.
YES | 2021 | 11 | 9 | 13:30 | 16:30 | 3:00 | Wrote remarks (comments) in SWAP_CYLNDRS program. Transcribed the SWAP_CYLNDRS program to a .txt file. Began notes and outlining for the development guide for SWAP_CYLNDRS.
YES | 2021 | 11 | 11 | 13:00 | 15:15 | 2:15 | Prepared & made current the Project Timestamp document. Began writing the Project Thesis document.
YES | 2021 | 11 | 16 | 12:45 | 13:45 | 1:00 | Completed notes and outlining for the development guide for SWAP_CYLNDRS. Began working on the development guide for SWAP_CYLNDRS. Prepared references for DRAW project. Left early for Covid Shot #2.
YES | 2021 | 11 | 18 | 13:00 | 14:30 | 1:30 | Finished the Introduction of the SWAP_CYLNDRS Program Development Guide.
YES | 2021 | 11 | 30 | 13:30 | 15:15 | 1:45 | Began the Procedure of the SWAP_CYLNDRS Program Development Guide. Wrote about writing an algorithm for the program.
YES | 2021 | 12 | 2 | 13:45 | 15:15 | 1:30 | Continued the Procedure of the SWAP_CYLNDRS Program Development Guide. Wrote about the necessity of commenting programs and the step of teaching frames.
NO | 2021 | 12 | 8 | 18:00 | 21:30 | 3:30 | Continued the Procedure of the SWAP_CYLNDRS Program Development Guide.
YES | 2021 | 12 | 9 | 13:00 | 15:00 | 2:00 | Continued the Procedure of the SWAP_CYLNDRS Program Development Guide. All progress during these two hours was lost because the laptop battery died and the file was wiped due to the setup of University laptops.
NO | 2021 | 12 | 9 | 22:00 | 24:00 | 2:00 | Continued the Procedure of the SWAP_CYLNDRS Program Development Guide.
NO | 2021 | 12 | 10 | 0:00 | 4:00 | 4:00 | Finished the Procedure of the SWAP_CYLNDRS Program Development Guide.
| 2021 |  |  |  |  | 0:00
| 2021 |  |  |  |  | 0:00 |  | Initial Learning
| 2021 |  |  |  |  | 0:00 |  | 12:30
| 2021 |  |  |  |  | 0:00 |  | Writing SWAP_CYLNDRS
[5 empty] | Supervised Hours | 1899-12-31 11:00 |  | 12:30
[5 empty] | Total Hours | 1899-12-31 20:30 |  | Writing Development Guide
19:30
Formulas:
Total Time = SUMIFS(G2:[Total Time, row above], A2:[In Lab?, row above], "YES")